## Model Program
Time | Program | Speaker
10-15 minutes | Welcome and Sponsor Recognition | National leader, chapter president, YLD representative
60 minutes | Three (3) "Ted Talks" | Younger professionals--call for presentations based on suggested topics
45-60 minutes | Keynote with/without Q&A | Judge, notable attorney
60 minutes | Networking Reception | Closing remarks by welcome group

## Timeline
Weeks Out | Date (Fill-In) | Task Detail | Task Type
28 Weeks |  | Identify Planning Committee | Logistics
24 Weeks |  | Confirm Venue & Date | Logistics
23 Weeks |  | Save the Date | Marketing
23 Weeks |  | Open Call for Presentations (Optional) | Logistics
23 Weeks |  | Publish Webpage | Logistics
22 Weeks |  | Sponsorship Sales Outreach | Sponsor
18 Weeks |  | Finalize Panel Topics | Logistics
14 Weeks |  | Confirm Speakers | Logistics
12 Weeks |  | Open Registration | Logistics
12 Weeks |  | Launch Marketing Campaign | Marketing
6 Weeks |  | Publish E-Flyer (Optional) | Marketing
4 Weeks |  | Submit CLE Applications (Panel Materials Due) | CLE
4 Weeks |  | Early Bird Registration Deadline (Optional) | Logistics
3 Weeks |  | Venue Logistics (Catering, AV) | Logistics
2 Weeks |  | Onsite Program + Signage (Optional) | Marketing
1 Week |  | Close Pre-Registration | Logistics
1 Week |  | Print + Assemble Event Materials | Logistics
- |  | EVENT DATE | -
(+) 1 Week |  | Report CLE Attendance + Certificates | CLE
(+) 1 Week |  | Post-Event Evaluation | Logistics
(+) 4 Weeks |  | Financial Reconciliation | Logistics

## Marketing
Social Media Promotion | Weeks Out
Save the Date | 23
Registration Open | 12
Agenda Announced (+ E-Flyer) | 6
Early Bird Deadline | 4
Keynote Speaker | 3
Sponsor(s) Feature | 2
Registration Closing | 1
Email Promotion | Weeks Out
Save the Date | 23
Registration Open | 12
Agenda Announced (+ E-Flyer) | 6
Early Bird Deadline | 4
Keynote Speaker | 3
Sponsor(s) Feature | 2
Registration Closing | 1
Collateral | Weeks Out
Graphics Package | 28
PPT Template | 28
E-Flyer | 6
Onsite Signage (Optional) | 2
Onsite Program | 2

## Logistics
✔ | Venue Coordination
Catering
Audio Visual
Parking/Arrival Info
Payment Schedule
✔ | Program Content (Webpage)
Event Description
Registration Rates
Sponsorship Tiers
Panels + Speakers
Qty CLE Credit
POC for Questions
✔ | Panel Coordination
Speaker Invitations
Speaker Confirmation
| Speaker Details | Name, Position, Organization, Email, Headshot, Bio
CLE Material Deadline
Final Presentation Materials
Complimentary Registration
✔ | Packing/Printing
Onsite Program
Signage
Membership Collateral
Name Badges
CLE Paperwork
Panel PPTs (USB)
Keynote/Speaker Gift(s)
Welcome/Lunch Script(s)
Camera
Speaker Table Tents
Onsite Registration Paperwork
Office Supplies
Printer + Paper
Sponsorship Deliverables
✔ | Attendee Communication
| Welcome Email | Venue arrival, dress code, panel materials, CLE instructions
Post-Event Evaluation
CLE Certificates/Reporting Update

## Sponsorship
Sponsorship Deliverables
Breakfast/Break Signage
Luncheon/Reception Signage
Remarks @ Selected Session
Logo v Name on Event Materials
Complimentary/Discount # Sponsor Firm Tickets
Ad in Chapter Newsletter
Social Media Post on Chapter Feed
Pre / Post Attendee List
Recognition at Podium
Flyer Distributed at Reg Desk
Exhibit Table
Steps
Sales Outreach
Sign Agreement
Email w/ Deliverables, Deadlines, Invoice
Deliverable Check-In (What's Outstanding?)
Thank You Message (Confirm Paid)
Notes
Mindful of keynote speaker ethics regulations (judge, public sector)
Secure logos ASAP (inclusion in e-flyer)
Can charge more for exclusive, but fewer sales opportunities