When a School Hosts a Naturalization Ceremony

The following pages are a planning guide from Citizenship Counts that has been slightly modified by the Educational Outreach function of the Administrative Office of the U.S. Courts for use by schools participating in the federal courts’ Constitution Day and Citizenship Day national initiative. It is important to keep in mind that the players, process, and program will vary somewhat depending on court practices and school policies.

# Planning Time Line

Schools that have hosted ceremonies report that they start planning about 14 weeks in advance of the ceremony.

# Naturalization Ceremonies Presided Over by a Federal Judge

The information here is a general guide for naturalization ceremonies presided over by a federal judge.  At a judicial ceremony, a federal court judge administers the Oath of Allegiance.  The U.S. Citizenship and Immigration Services (USCIS) also is authorized to conduct naturalization ceremonies that are called administrative ceremonies.  In an administrative ceremony an official from USCIS, administers the Oath of Allegiance.

Contact People – One Per Participating Entity:  It is recommended that each entity designate one contact person/decision maker and that communication among the entities be limited to these representatives.  The court coordinator is the only person with whom the school representative needs to communicate. Your contact at the court is usually, but not always, a Naturalization Ceremony Clerk or a clerk in the District Clerk’s office.  That person/coordinator will handle communication with the other parties – U.S. Marshals Service, USCIS, etc. Your court contact will provide you with the relevant information from the court and the other parties.

# Non-School Participants and Their Roles

Federal Court in Your Jurisdiction:

- Designates a court contact for you who is the key decision maker regarding the program.

- Provides the presiding judge for the ceremony.  The judge welcomes everyone, administers the oath, and makes some remarks.  Sometimes, the judge poses for photos afterward.

U.S. Marshals Service

- Provides the judge’s security and works with the school contact, the school’s chief security contact, and local police.

- Security.  Identify and designate the on-campus security decision maker.  That person will participate in site visits and will work closely with the U.S. Marshals Service and local law enforcement on the planning and implementation of security measures at the school site in advance of, during, and immediately after the ceremony

Page 1

U.S. Citizenship and Immigration Services

- Only the court contact interfaces with the U.S. Citizenship and Immigration Service (USCIS).  They work together on all matters related to the candidates – inviting them, communicating with them about the ceremony, and processing them with their paperwork at the event.

# Identify Decision Makers Who Will Represent the Participating Entities

The Following Entities Should Have a Decision Maker Representing It at Meetings and at the Event

These individuals have the authority to make decisions, give approvals, assign tasks, and access their organization’s services.

- School. Two Contact People:  1) The school administration’s primary decision maker and the 2) school’s security decision maker represent the school’s interests and make decisions about campus logistics.

- U.S. District Court.  One Contact Person:  Works with the school’s primary decision maker.  In addition to representing the court, the court contact provides information to the School’s Primary about relevant information related to U.S.C.I.S.

- USCIS.  One Contact Person. Works with the U.S. District Court contact person.  The court contact person communicates relevant information about U.S.C.I.S. to the School’s Primary Contact.

- U.S. Marshals Service.  One Contact Person: Works with the  U.S. District Court contact and the school’s security decision maker

- Community Representatives.   Light refreshments are totally optional – usually, coffee, tea, water, juice.  Most new citizens leave right after the ceremony to celebrate with family and friends. A representative could be invited from a group that might provide and serve refreshments.  The Daughters of the American Revolution or the American Association of University Women offer hospitality in some jurisdictions.  In some communities, the League of Women Voters set up a table for voter registration after the ceremony.

Five Meetings and Two Conference Calls.  The School Representative Calls Four Meetings at the School:

- Site Visit and Initial Planning:  The committee tours the facility and identifies the spaces that will be needed for the ceremony as well as the pre-ceremony and post-ceremony activities.

- Conference Call:  Progress  reports from all representatives

- Confirmation Meeting:  Finalize VIP reserved seating; stage set up. Confirm logistics and agree on media access and management plans.

- On-Site Meeting: Ceremony walk through on campus for partners.  Students who will be on stage join the walk through and rehearse.

- Media Walk Through:  On-site media tours the site right after the partners’ on-site meeting

- Conference Call:  Final confirmation of logistics on the checklist  with all partners

- Post-Event Debriefing:  Discussion of successes and lessons learned

Page 2

# Select the Ceremony Site on Campus

On-Campus Locations.  In a school setting, the auditorium, gymnasium, cafeteria, or athletic facilities are common sites for ceremonies.

Site Visit(s). Before finalizing the site decision and reserving the space, schedule a site visit with your court contact, who will reach out to include the U.S. Marshals Service and USCIS, as appropriate.  Campus security and local police should participate in the same site visit.

At the meeting, determine the seating capacity so that USCIS has the information needed to determine the number of candidates and an estimated number of candidates’ guests.

Considerations When Selecting the Venue

Date.  Ceremonies that are part of the federal courts’ national initiative in 2017 are scheduled the week of September 18. (Constitution Day and Citizenship Day officially is observed on September 17, which is a Sunday this year.)

Time.   Depending on the number of candidates, how the ceremony is conducted, and the length of the program, the event takes about one hour. When setting the time for the event, start with your court contact who will ascertain the availability of the judge and the U.S. Marshal.

Capacity:   The ceremony space should have enough seating capacity for the new citizens, plus two or three seats for guests of each candidate; federal court personnel; students; faculty; staff,  interested parents, and special guests.

Parking.  Reserve and mark spaces for the judge; one court staff person; the U.S. Marshal; guest speaker, if one is scheduled, and other special guests.  Make the court contact aware of the parking area for the new citizens and their guests.  Provide signage at the site.

Access.  Make the necessary arrangements to accommodate the needs of everyone – in the building and in the parking arrangements.

News Media and New Media. The court contact can advise on the court’s policy for media coverage at the ceremony. Coordinate media advisories and news releases with your court contact.  A template will be provided to the court contact.  Ask your court contact if he/she can get authorization for the student media (school newspaper, yearbook, website, broadcast, bloggers, etc.) to cover the event.

Weather.  Make a contingency plan for bad weather or other disruption.

Page 3

Areas to be Reviewed During the First Site Visit by the Planning Committee

- Check-in Area and Waiting Room for Candidates.  All candidates must sign in. Many schools reserve the library, multi-purpose room, or another room with chairs and a door that can be closed.  USCIS officials conduct a roll call and give instructions for the ceremony.

- Waiting Room for the Presiding Judge. A separate, nearby space is where the judge will wait prior to the ceremony.  The U.S. Marshal should have input on the selection of this space during the site visit.

- Stage Area.  AV equipment needs include a podium with a microphone; two standing microphones on the stage are for use by the judge, the speakers, and any performers.  Seating on the stage is for the judge and other speakers.

- Audience Area.  In advance, the school and the court contact develop and share with the planning committee the seating chart for the stage.  They also produce a seating chart for the audience with designated areas for the candidates, special guests, and students.

- Reserved Media Space.  Media and student journalists covering the event need designated, reserved areas.

- Reception Area.  A space is designated for candidates, guests, officials, and students to gather after the ceremonies.  Students and other well-wishers interact with the new citizens; journalists conduct interviews.  Light refreshments are optional and, typically, are sponsored by a group such as the Daughters of the American Revolution, League of Women Voters, etc.  In the reception room, students have the opportunity to interact with the new citizens. Media interviews, typically, are allowed in this space.

Audio-Visual Requirements

- Public Address System.  Use a well-tested sound system and have back-ups for the different components, including batteries and microphones, at the event.

- On-Stage Requirements.  The podium has a microphone; the stage has two standing microphones.  A handheld microphone is available at the podium.

- Media Needs.  In advance of the program, ask a television reporter what the print and broadcast media need to cover the event.  Make the media contact aware of ground rules or restrictions.

Ask the media to bring its own mult box.

Page 4

# For Teachers:  Ways to Prepare and Involve Students

Dress Code and Decorum.  Appropriate attire is dresses, skirts, long pants and dress shirts or collared T-shirts. Not allowed:   Sunglasses, hats, shorts, T-shirts with messages, revealing or tight-fitting clothing.

Teacher Resources

A how-to podcast is available for teachers to help them prepare their students. General information  is posted in the Educational Resources section of the federal courts’ website.  Program-specific resources are included in the attachments to this e-mail. Courts, typically, involve students in the event by giving their schools the opportunity to sing the National Anthem, lead the Pledge of Allegiance, recite the Preamble to the Constitution, and/or deliver hand-written welcome letters to the new citizens after the ceremony.

Use Multi-Media Resources to Enhance Understanding of, and Pride in, Citizenship

To see more examples of naturalization ceremonies conducted across the nation, view the four-minute video America, the Beautiful Mosaic.

Every year, the Administrative Office of the U.S. courts produces a video roundup of the theme as it is communicated in ceremonies across the natio

- Theme – Ceremonies at Courthouses and Community Sites 2014

- Theme -- Iconic Sites 2015

- Theme -- National Parks 2016

- Theme – Naturalization Ceremonies at Schools 2017 --  To be posted in October, 2017

Events Address Common Core and the Congressional Mandate

Observing or participating in naturalization ceremonies on Constitution Day and Citizenship Day are activities that support Common Core’s C3 focus on college, career, and civic life.

The ceremonies also help schools respond to a Congressional mandate to teach about the Constitution on September 17 every year.  In 2004, Congress mandated that schools receiving federal funding provide education about the Constitution on that date.

‘‘(b) 	Each educational institution that receives Federal funds for a fiscal year shall hold educational program on the United States Constitution on	September17 of such year for the students served by the educational institution.”

Page 5

# Preparing the Site for the Ceremony

Facilities and Space Requirements

  - Check-in Area for Candidates.  All candidates must sign in. When the court representative and U.S. Marshal come for their site visit, they can help identify a space for the waiting area and sign-in table. Many schools reserve the library, multi-purpose room, or lobby for this purpose. During the check in, the room cannot be used for any other purpose.

- Waiting Room for Candidates Only.  The check-in area, furnished with chairs, can serve as the waiting room, for the candidates only. In this space, USCIS officials can conduct a roll call and give instructions for the ceremony.

- Waiting Room for the Presiding Judge. A separate, nearby space is where the judge will wait prior to the ceremony.  The U.S. Marshal should be shown this space and agree to it during the site visit.

- Stage Area – Seating and AV Equipment.  On the stage, the AV equipment should include a podium with a microphone for the presiding judge; and a standing microphone that is for speakers and performers.  A handheld microphone is a good idea to have on hand as a backup.

- Audience Area.  In advance, develop and share with the planning committee the seating chart for the stage and for the audience area.

- Reception Area.  A space is designated for a gathering after the ceremony where students and other well-wishers can interact with the new citizens and where journalists can do live interviews.

Seating Arrangements

Seating Chart.  A chart helps student ushers and audience members find their designated seating areas.

Reserved Seating on the Stage

- Judge and others, including:  Court officials, special guests, elected officials.

In the Audience

- Candidates for citizenship

- Candidates who are in the military are seated in the front row

- Families and guests

- Accommodations for persons with disabilities

- Students

- Faculty – It’s a good idea to reserve faculty seats among the students.

- Media

Page 6

Flags Display – Opportunity for Student Color Guard

Three flags must be displayed during the ceremony -- the United States flag, the state flag, and the USCIS flag.  The flags are posted according to a specific protocol that the court contact can share in advance.

- The colors may be presented by selected students; ROTC; Scouts; or the military.

- Check with the USCIS to find out if it will provide miniature U.S. flags to the new citizens.

Audiovisual Equipment and Needs

The sound system and microphones should be tested two weeks in advance so that replacements can be provided, if necessary.  All equipment should be tested, again, on the day of the event.

- Two Microphones:  One microphone is at the podium for the judge.  A stand-up microphone is at the middle of the stage for performers.

- Video Screen Set Up:  If video(s) will be shown.

# Elements of the Ceremony

Naturalization ceremonies usually follow the same order of business as listed here.

- Students Lead the Audience in Singing the National Anthem.

- Students Recite the Preamble to the Constitution.

- The school principal welcomes everyone to the school.

- The Clerk of Court asks everyone to rise as the judge enters the room.  The judge makes brief welcoming remarks.

- The Clerk of Court acknowledges special guests and ceremony participants and gives an overview of what will happen during the ceremony.

- Remarks by officials and guests do not include partisan or political statements, religious content, or inappropriate or offensive references.

- Address/Remarks by  the Speaker

- The presiding judge makes remarks.

- Presentation of Candidates

- The Clerk of Court presents the candidates for naturalization to the judge who administers the Oath of Allegiance. Suggested language includes: “At this time, it is my privilege to present (insert number) applicants for naturalization from (insert number) countries.  Each applicant has been examined by a USCIS officer and found to be eligible for naturalization.”

Page 7

- Roll Call

Option A

- In some instances, the Clerk of Court reads the list of countries represented and asks candidates to stand when the name of the country is announced.

- They remain standing until the Oath of Allegiance is administered.

Option B

- If a large group is being naturalized, the Clerk of Court makes a brief statement including the number of people receiving their citizenship and the names of their countries of origin.

Accommodation.  Arrangements should be made for candidates with disabilities and other persons who are unable to stand during the roll call.

- Administration of the Oath of Allegiance  -- By the Presiding Judge

The words of the Oath of Allegiance can be included in the printed ceremony program.

"I hereby declare, on oath, that I absolutely and entirely renounce and abjure all allegiance and fidelity to any foreign prince, potentate, state or sovereignty, of whom or which I have heretofore been a subject or citizen; that I will support and defend the Constitution and laws of the United States of America against all enemies, foreign and domestic; that I will bear true faith and allegiance to the same; that I will bear arms on behalf of the United States when required by the law; that I will perform noncombatant service in the armed forces of the United States when required by the law; that I will perform work of national importance under civilian direction when required by the law; and that I take this obligation freely without any mental reservation or purpose of evasion; so help me God."

- Presentation of Certificates of Naturalization  -- By the Presiding Judge and a Clerk

- After the group takes the Oath, each candidate’s name is called and he/she walks to the judge and clerk of court to receive the certificate.

- The Pledge of Allegiance  -- Opportunity for Student Involvement  (leading the pledge)

- The new citizens are asked to recite the Pledge of Allegiance to the flag.

- A student or a student group may lead the pledge.

- Supreme Court Associate Justice Sonia Sotomayor’s Five-Minute Message

New citizens watch a video welcome message from the President of the United States.

11.  A student choir may sing a patriotic song at the conclusion of the ceremony.

Page 8

# Optional Elements

The following ideas are suggestions that can be incorporated into the program to enhance the atmosphere during the naturalization ceremony.

Program for Naturalized Citizens and Guests

As a welcoming gesture, some schools create a commemorative program for everyone in attendance, if USCIS 	or the court approves your request to do so.  It’s an opportunity to be creative and include artwork from 	students, a world map that highlights where the naturalized citizens came from, essays about why your 	students are proud to be American citizens, etc.

Invitations

- The naturalization ceremony is an opportunity to welcome school board members, local elected officials, and others to your campus.

- Invitations should be sent out either by mail or e-mail at least three weeks prior to the ceremony.

Directional Signage or Volunteer Guides

- Directional signage or student volunteers should be provided to guide the candidates to their check-in location and to direct guests to their seats.

Parking and Carpooling

- The venue should take measures to ensure there is adequate parking for the new citizens and their guests.  In addition, VIP parking spots should be reserved for USCIS, the judge (if needed), the guest speaker, and any special guests such as district office staff and elected officials.

- If there is a nearby park, businesses, or church/temple, inquire whether they will allow you to use their parking for this special event.  If so, it is best to have the school staff and students park in the borrowed lots and reserve parking on the premises for the new citizens and special guests.

Congratulatory Messages for New Citizens

- If the circumstances permit, students and faculty can write short congratulatory messages to the new citizens.  These messages can be given from one student to one new citizen at the end of the program.  The letter can be souvenir from the occasion.

- Students can create congratulatory and welcoming posters, with patriotic themes, to display around the school on the day of the ceremony.

Videography and Photography

- Some schools videotape the ceremony and take photographs as well, as permitted by USCIS and the court.  This is a great project for a photography/videography class.  The student newspaper and yearbook can be invited and encouraged to take photographs and cover the event for their respective student publications.

- Some excellent photo opportunities for students to take include the following: The citizens raising their right hand while taking the Oath of Allegiance, student participation in the program, candids of new citizens celebrating with families, etc.

Page 9

- Photos/video footage taken during the ceremony can be used by the media or the Administrative Office of the U.S. Courts for educational purposes. Please make sure that all participating students have submitted a photo release, signed by their legal guardians.

Special Voter and Social Security Registration Area

- USCIS will likely ask for a table to be set up where the candidates for naturalization can register for their social security cards, and register to vote. This table can be set up outside the room where the ceremony is being held, in the same area as the post-ceremony reception, or in another location that is easily accessible to the new citizens.

# Meet and Greet

Schools, often, host a post-ceremony gathering so that students can engage with the new citizens.

- For privacy reasons, invitations to the reception cannot be extended to the candidates prior to the ceremony. However, during the welcome, the principal can announce the gathering and encourage attendance.

- Note:  Many new citizens will be on their way to their own celebrations after the ceremony, but some will stay for a few minutes.

# Student Interviews

During the reception students can meet and talk with the new citizens.

# Working with the Media

The news media often covers naturalization ceremonies, particularly when the event is conducted at a location outside the courthouse.  Feel free to notify the media about your plans.

- If your school or school district has a media contact or designated spokespersons, keep them informed of the plans from the beginning.  They will have ideas that will increase the likelihood of coverage.  They also will know what logistical set up the media needs.

- One person, often the school principal, should be designated to be interviewed by the media about the event.

- Create a media sign-in sheet and assign a school staff person to assist reporters throughout the event.

- School journalists – print, web, and video – may cover the event.

# Page 10

# Follow Up

# Thank-you letters should be sent to everyone who contributed to the success of the naturalization ceremony. Examples of people to thank include:

1. USCIS staff

2. Judge and U.S. federal courts staff (if applicable)

3. Guest speakers

4. Community members

5. All donors and sponsors

The thank you letters could be generated by students or the committee chairperson.  The thank you notes can include photos or artwork from the ceremony, which makes the experience even more meaningful.

# Links

U.S. Citizenship and Immigration Services (USCIS)

This is the official site for information related to naturalization and immigration issues.

The Federal Courts

This website provides educational resources for Constitution Day and Citizenship Day;

naturalization ceremonies; and other court literacy topics.

League of Women Voters Guide

This guide explains the naturalization ceremony as an event and how the League of Women Voters can help with voter registration after the ceremony.

# Page 11